## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Abby | 6000 | 1750 | 4250 | 0 | 0 | 0 | 1000 | 750 | 250 | 0 | 0 | 0 | 5000 | 1000 | 4000
Bill | 7400 | 2200 | 5200 | 700 | 600 | 100 | 1000 | 600 | 400 | 700 | 500 | 200 | 5000 | 500 | 4500
Carley | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1000 | 600 | 400 | 0 | 0 | 0 | 5000 | 2200 | 2800
Dan | 6000 | 3400 | 2600 | 0 | 0 | 0 | 1000 | 600 | 400 | 0 | 0 | 0 | 5000 | 2800 | 2200
Erin | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1000 | 750 | 250 | 0 | 0 | 0 | 5000 | 1600 | 3400
Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5000 | 3300 | 1700 | 700 | 500 | 200 | 25000 | 8100 | 16900

## Gantt
| predicted time(hrs) | time spent(hrs) | % Complete | Status |  | Key: | complete | this week | planned | slack
TL1: |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Setting up Godot |  |  |  | planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
Totals | 0 | 0
TL2: Austin |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Setting up Godot | 1 | 1 | 100% | complete | 1: complete
Godot Training | 2 | 3 | 100% | complete | 2: complete; 3: complete; 4: complete
Platformer¦Outside Meetings | 4 | 2 | 50% | this week | 5: this week; 6: this week; 7: this week; 8: this week
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
Totals | 7 | 6
TL3: |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Setting up Godot |  |  |  | planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
Totals | 0 | 0
TL5: |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Setting up Godot |  |  |  | planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
Totals | 0 | 0
TL6 : |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Setting up Godot |  |  |  | planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
planned
Totals | 0 | 0
group totals (hrs) | #REF! | #REF!
group totals ($) | #REF! | #REF!

## Meetings
| Date | 2023-08-29 | 2024-09-03 | 2024-09-05 | 2024-09-17 | 2024-09-12
| Purpose | First Meeting (in class) | Initial Platformer Planning | Platformer Prep | Platformer Prep | Group RFP Prep | SA Prep | SA Prep
| Hours | 1 | 1 | 1 | 1 |  | 1.5 | 2
Nate | 7.5 | ü | ü | ü | ü | ü | ü | ü
Austin | 6 | ü | ü | ü | ü |  |  | ü
Ankeet | 6 | ü | ü | ü | ü | ü |  | ü
Clayton | 6 | ü | ü | ü | ü | ü |  | ü
Sohan | 7.5 | ü | ü | ü | ü | ü | ü | ü
Total | 33 | 5 | 5 | 5 | 5 | 0 | 3 | 10 | 0 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Nate | SA Individual schedule | bar: 1 to 2
Champion | bar: 3 to 7
RFP | bar: 8 to 9
| Subtotal | 0 | 0
Austin | SA Individual schedule | 4 | 1
| Champion | 2 | 3
| RFP | 1 | 1
| Subtotal | 7 | 5
Ankeet | SA Individual schedule | bar: 1
Champion | bar: 2 to 7
RFP | bar: 8
| Subtotal | 0 | 0
Sohan | SA Individual schedule | bar: 1 to 2
Champion | bar: 3 to 7
RFP | bar: 8 to 9
| Subtotal | 0 | 0
Clayton | SA Individual schedule | bar: 1 to 3
Champion | bar: 4 to 8
RFP | bar: 9
Subtotal |  | 0 | 0
Total |  | 7 | 5

## Overhead
| Abby | Bill | Carley | Dan | Erin | Fred | George
SA Presentation Prep | 0 | 5 | 0 | 8 | 0 | #REF! | #REF!
Software Development Specialists Presentation Prep (group presentation) | 4 |  | 9 | 4 | 6 | 4 | 5
Team Lead Presentation Prep (individual presentation) | 6 |  | 7 | 12 | 6 | 7 | 8
Oral Exam Prep |  |  | 4 | 4 | 4 | 4 | 3
Post Mortum Presentation Prep |  |  | 2
Total | 10 | 5 | 22 | 28 | 16 | #REF! | #REF!