## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead |  |  | Magic Numbers
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Wage
Nate | 13300 | 8500 | 4800 | 5900 | 3000 | 2900 | 1500 | 3500 | -2000 | 900 | 800 | 100 | 5000 | 1200 | 3800 | 100
Austin | 12700 | 9060 | 3640 | 5500 | 2760 | 2740 | 1500 | 3700 | -2200 | 700 | 500 | 200 | 5000 | 2100 | 2900
Ankeet | 13500 | 9600 | 3900 | 6000 | 3000 | 3000 | 1500 | 2800 | -1300 | 1000 | 1000 | 0 | 5000 | 2800 | 2200
Clayton | 10400 | 7600 | 2800 | 3900 | 3700 | 200 | 1500 | 3300 | -1800 | 0 | 0 | 0 | 5000 | 600 | 4400
Sohan | 13200 | 5800 | 7400 | 5900 | 3000 | 2900 | 1500 | 2100 | -600 | 800 | 700 | 100 | 5000 | 0 | 5000
Total | 63100 | 40560 | 22540 | 27200 | 15460 | 11740 | 7500 | 15400 | -7900 | 3400 | 3000 | 400 | 25000 | 6700 | 18300

## Gantt
| predicted time(hrs) | time spent(hrs) | % Complete | Status |  | Key: | complete | this week | planned | slack
TL1: Nathan |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Requirements Collection | 10 | 8 | 80% | complete | 1: complete; Key: 2: complete; complete 3: complete; this week 4: complete; planned 5: complete; slack 6: complete; slack 7: complete; slack 8: complete
Report Design | 10 | 8 | 80% | complete | slack 9: complete; slack 10: complete; slack 11: complete; slack 12: complete; slack 13: complete; slack 14: complete; slack 15: complete; slack 16: complete; slack 17: slack; slack 18: slack
Level Difficultly Tables | 6 | 4 | 66.67% | complete | slack 19: complete; slack 20: complete; slack 21: complete; slack 22: complete; slack 23: complete; slack 24: complete
Level Data Object design | 2 | 2 | 100% | complete | slack 9: complete; slack 10: complete; slack 11: complete; slack 12: complete; slack 13: complete; slack 14: slack; slack 15: slack; slack 16: slack; slack 17: slack; slack 18: slack; slack 19: slack; slack 20: slack; slack 21: slack; slack 22: slack; slack 23: slack; slack 24: slack
User Documentation | 2 | 1 | 50% | this week | [8 empty] | this week | this week | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack | slack
Programming difficulty Calculator | 3 | 3 | 100% | complete | slack 25: complete; slack 26: complete; slack 27: complete
Replacing RoundStatusTracker Class | 2 | 1 | 50% | complete | slack 25: complete; slack 26: complete; slack 27: slack
Change LevelData/LevelDifficultlyTable to Resources | 2 | 1 | 50% | complete | slack 25: complete; slack 26: slack; slack 27: slack
Integrating Chicken Spawning | 6 | 0 | 0% | this week | slack 28: this week; slack 29: this week; slack 30: this week; slack 31: this week; slack 32: this week
LevelData Serialization Support | 10 | 1 | 10% | planned | slack 33: planned; slack 34: planned; slack 35: planned; slack 36: planned; slack 37: planned; slack 38: planned; slack 39: planned; slack 40: planned; slack 41: planned; slack 42: planned; slack 43: planned
Testing | 5 | 1 | 20% | this week | slack 25: this week; slack 26: this week; slack 27: this week; slack 28: slack; slack 29: slack; slack 30: slack; slack 31: slack; slack 32: slack; slack 33: slack; slack 34: slack; slack 35: slack; slack 36: slack; slack 37: slack; slack 38: slack; slack 39: slack; slack 40: slack; slack 41: slack; slack 42: slack; slack 43: slack
Installation | 1 | 0 | 0% | planned | slack 44: planned
| 0 | 0 | 0% | planned
Totals | 59 | 30
TL2: Austin |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Requirements Collection | 5 | 5 | 100% | complete | 1: complete; 2: complete; 3: complete; 4: complete; 5: complete
Plan Dynamic Binding | 2 | 1 | 50% | complete | 6: complete; 7: complete; 8: slack; 9: slack; 10: slack; 11: slack; 12: slack; 13: slack; 14: slack; 15: slack; 16: slack; 17: slack; 18: slack; 19: slack; 20: slack; 21: slack
Plan Pattern | 2 | 1 | 50% | this week | 6: this week; 7: this week; 8: slack; 9: slack; 10: slack; 11: slack; 12: slack; 13: slack; 14: slack; 15: slack; 16: slack; 17: slack; 18: slack; 19: slack; 20: slack; 21: slack
Tower Zones Design | 6 | 2 | 33.33% | this week | 6: this week; 7: this week; 8: this week; 9: this week; 10: this week; 11: this week; 12: slack; 13: slack; 14: slack; 15: slack; 16: slack; 17: slack; 18: slack; 19: slack; 20: slack
Level Management Design | 10 | 4 | 40% | this week | 6: this week; 7: this week; 8: this week; 9: this week; 10: this week; 11: this week; 12: this week; 13: this week; 14: this week; 15: this week
Find/Create Backgrounds | 8 | 1 | 12.5% | planned | 1: planned; 2: planned; 3: planned; 4: planned; 5: planned; 6: planned; 7: planned; 8: planned; 9: slack; 10: slack; 11: slack; 12: slack; 13: slack; 14: slack; 15: slack; 16: slack; 17: slack; 18: slack; 19: slack; 20: slack
Design Maps | 5 | 2 | 40% | this week | 12: this week; 13: this week; 14: this week; 15: this week; 16: this week; 17: slack; 18: slack; 19: slack; 20: slack; 21: slack; 22: slack; 23: slack; 24: slack; 25: slack
Level Management Programming | 10 | 7 | 70% | this week | 16: this week; 17: this week; 18: this week; 19: this week; 20: this week; 21: this week; 22: this week; 23: this week; 24: this week; 25: this week
Tower Zone Programming | 3 | 1 | 33.33% | planned | 12: planned; 13: planned; 14: planned; 15: planned; 16: slack; 17: slack; 18: slack; 19: slack; 20: slack; 21: slack; 22: slack; 23: slack; 24: slack; 25: slack
Testing | 2 | 3.5 | 175% | planned | 26: planned; 27: planned
User Documentation | 2 | 0.1 | 5% | this week | 26: this week; 27: this week
|  |  | 0% | planned
|  |  | 0% | planned
|  |  | 0% | planned
Totals | 55 | 27.6
TL3: Ankeet |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Godot Background Basics | 4 | 4 | 100% | complete | 1: complete; 2: complete; 3: complete
Requirements Collection | 4 | 4 | 100% | complete | 4: complete; 5: complete; 6: complete; 7: complete; 8: complete; 9: complete
Tower Integration System | 8 | 5 | 62.5% | this week | 10: this week; 11: this week; 12: this week; 13: this week; 14: this week; 15: this week; 16: this week; 17: this week
Tower Deployment | 6 | 3 | 50% | this week | 18: this week; 19: this week; 20: this week; 21: this week; 22: this week; 23: this week
Tower Database Construction | 8 | 4 | 50% | this week | 18: this week; 19: this week; 20: this week; 21: this week; 22: this week; 23: this week; 24: this week; 25: this week; 26: slack; 27: slack; 28: slack; 29: slack
User Documentation | 4 | 1 | 25% | planned | 18: planned; 19: planned; 20: planned; 21: planned; 22: planned; 23: planned; 24: planned; 25: planned; 26: planned; 27: planned
Programming | 10 | 4 | 40% | this week | 24: this week; 25: this week; 26: slack; 27: slack; 28: slack; 29: slack; 30: slack; 31: slack; 32: slack; 33: slack
Testing | 8 | 4 | 50% | this week | 34: this week; 35: this week; 36: this week; 37: this week; 38: this week; 39: this week; 40: this week
Installation | 4 |  | 0% | planned | 40: planned; 41: planned; 42: planned; 43: planned
Learning C# | 4 | 1 | 25% | this week
|  |  | 0 | planned
Totals | 60 | 30
TL5: Clayton |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Define Functions | 2 | 2 | 100% | complete | bar: 1 to 2
Collab with Team | 4 | 10 | 250% | complete | bar: 3 to 6
Organize workspace | 4 | 4 | 100% | complete | bar: 3 to 6
Character Design | 3 | 2 | 66.67% | this week | bar: 7 to 9
User Documentation | 6 | 5 | 83.33% | planned | bar: 7 to 17
Character Programing | 8 | 7 | 87.5% | planned | bar: 7 to 14
Testing / Misc Programing | 8 | 5 | 62.5% | planned | bar: 7 to 14
Testing Features | 3 | 2 | 66.67% | planned | bar: 15 to 17
Installation / Final Integration | 1 | 0 | 0% | planned | bar: 18
|  |  | 0% | planned
|  |  | 0% | planned
|  |  | 0% | planned
Totals | 39 | 37
TL6 : Sohan Lama |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Requirements Collection | 10 | 6 | 60% | complete | bar: 1 to 6
UI Design (Main Menu) | 6 | 4 | 66.67% | this week | bar: 7 to 12
UI Design (Tower Selection) | 6 | 6 | 100% | complete | bar: 13 to 18
Programming Main Menu | 12 | 4 | 33.33% | planned | bar: 19 to 24
Programming Tower Selection | 8 | 4 | 50% | this week | bar: 25 to 29
Testing UI functionality | 6 | 2 | 33.33% | planned | bar: 30 to 35
Final Documentation | 6 | 1 | 16.67% | planned | bar: 36 to 39
HealthBar (Design) | 1 | 1 | 100% | complete | bar: 40 to 42
HealthBar (Programming) | 4 | 2 | 50% | this week | bar: 43 to 46
|  |  | 0% | planned
|  |  | 0% | planned
|  |  | 0% | planned
|  |  | 0% | planned
|  |  | 0% | planned
Totals | 59 | 30
group totals (hrs) | 272 | 154.6
group totals ($) | 27200 | 15460
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I fixed your part of the chart so it should auto update. Just click the drop down and select the status of the task. To edit the bars, set anything other than slack to the status cell. Set any cells you want to be slack time to the slack cell in the legend (=$K$1)
Note on A34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Delete, covered in meetings Reply: The tutorials from platformer presentations
Note on A40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs to be separated out into what will be programmed
Note on A42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What is being installed?
Note on AS42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why is this just slack time?
Note on A48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Delete, covered in meetings tab
Note on A52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Separate into what will be programmed
Note on A55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What will be installed?
Note on A56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What will be installed?
Note on A57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: need to add time for dynamic binding and patterns
Note on B59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is probably the minimum amount of time we want to have planned. If you need some padding maybe add some to the different categories of programming.
Note on A71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: need to add time for dynamic binding and patterns

## Meetings
Date |  | 2023-08-29 | 2024-09-03 | 2024-09-05 | 2024-09-17 | 2024-09-12 | 2024-09-19 | 2024-09-25 | 2024-10-03 | 2024-10-16 | 2024-10-17 | 2024-10-24
Purpose |  | First Meeting (in class) | Training | Git Seminar | Unit Test Seminar | Group RFP Prep | SA Prep | MVP | Patterns Seminar | Gantt Team Building | Team Tests Integration | Weekly meeting
Hours |  | 5 | 25 | 10 | 5 | 8 | 10 | 30 | 5 | 5 | 28 | 6
Nate | 35 | 1 | 5 | 2 | 1 | 2 | 2 | 8 | 1 | 1 | 6 | 6
Austin | 37 | 1 | 5 | 2 | 1 |  | 2 | 8 | 1 | 1 | 10 | 6
Ankit | 28 | 1 | 5 | 2 | 1 | 2 | 2 | 3 | 1 | 1 | 6 | 4
Clayton | 33 | 1 | 5 | 2 | 1 | 2 | 2 | 8 | 1 | 1 | 6 | 4
Sohan | 21 | 1 | 5 | 2 | 1 | 2 | 2 | 3 | 1 | 1 |  | 3
Total | 154 | 5 | 25 | 10 | 5 | 8 | 10 | 30 | 5 | 5 | 28 | 23

## Software Analysis
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Nathan | SA Individual schedule | 4 | 2 | bar: 1 to 4
| Champion | 3 | 4 | bar: 5 to 7
| RFP | 2 | 2 | bar: 8 to 9
| Subtotal | 9 | 8
Austin | SA Individual schedule | 4 | 1 | bar: 1 to 4
| Champion | 2 | 3 | bar: 5 to 6
| RFP | 1 | 1 | bar: 7
| Subtotal | 7 | 5
Ankeet | SA Individual schedule | 5 | 4 | bar: 1 to 5
| Champion | 3 | 3 | bar: 6 to 8
| RFP | 2 | 3 | bar: 9 to 10
| Subtotal | 10 | 10
Sohan | SA Individual schedule | bar: 1 to 2
Champion | bar: 3 to 7
RFP | bar: 8 to 9
| Subtotal | 0 | 0
Clayton | SA Individual schedule | 3 | 3 | bar: 1 to 3
| Champion | 4 | 3 | bar: 4 to 7
| RFP | 1 | 1 | bar: 8
| Subtotal | 8 | 7
Total |  | 34 | 30

## Overhead
| Nate | Austin | Ankeet | Clayton | Sohan
Setting up Godot | 1 | 1 | 1 | 1 | 1
SA Presentation Prep | 2 | 5 | 10 | 2 | 0
Software Development Specialists Presentation Prep (group presentation) | 4 | 6 | 9 | 4
Team Lead Presentation Prep (individual presentation) | 6 | 10 | 9
Oral Exam Prep
Post Mortum Presentation Prep
Total | 12 | 21 | 28 | 6 | 0